## Sheet1
10. Issue Log
Issue | How it could have been prevented? | How to address this issue?
Cancelled planned meeting | Manage other work in regulation with planned meetings. | Hold virtual meeting whenever in-person meetings not feasible. Reschedule meetings as per team's availability.
Scope creep | Work with stakeholders to clearly identify requirements Set goals according to identified requirements | Updating the stakeholders regularly in regards with the progress of the project
Did not meet set Milestone deadlines | Frequent follow-up meetings Regular monitoring of deadlines by project manager | Discuss and review with the team and set realistic deadlines.
MS Project software configuration issue | Not applicable | Install alternate softwares such as Project Libre