## Sheet1
12. Lessons Learned
Progress Group | Start Doing | Stop Doing | Continue Doing
Initiating | Establish roles and responsibilities within the project team. Conduct meetings on time. Brainstorm with team meetings to get better output. Set a target for each meeting. | Procrastination. Identify and filter stakeholders ahead of the scope. | Research with intent helps understand the process better. Respect everyone's opinions on the team. Research and collaborate on tasks.
Planning | Set a realistic deadline for each task | Miss deadlines. Leave work incomplete | Regular team meetings to brainstorm ideas Follow-up about the progress with respective team members Create and set milestones
Executing | Assign team member responsibilities Maintain documentation for brainstormed activities | Expect to complete a document in one stretch Divide work unevenly | Follow WBS Keep stakeholders updated on progress Be mindful of change requests Proofread and verify content with the professor
Monitoring & Controlling | Ask for feedback from stakeholders | Operate outside the project scope | Regularly seek feedback from stakeholders
Closing | Verify that all requirements were met | Don’t assume project completion | Officially closeout project with stakeholders