## Sheet1
8. Communication Plan
Sr No. | Stakeholder | What | When | How | Who | Where
1 | Darksky | Obtaining sky quality index from Darksky organization | Monthly During Market Research phase | Online/Email | Team Aces | Email, Zoom, Webex
|  | Details regarding eco-friendly lights, outdoor/indoor lights | Once During Survey phase | Online/Email | Team Aces | Email, Zoom, Webex
|  | Guidelines & Policies regarding Light Pollution | Once During Survey phase | Online/Email | Team Aces | Email, Zoom, Webex
2 | Eco-friendly light suppliers | Discussing Potential Partnership | Monthly Post-Market Research phase | Online/Phone-call | Team Aces | Zoom, Webex, Office
|  | Contract Signing after getting funds | Once after Post-funding phase | In-person | Team Aces | Office
3 | Professor | Status of the Project | Monthly from kick-off to closing | Online/In-person | Team Aces | Zoom, Email, Classroom
|  | Issues during project | Weekly till 22nd April 2022 | Online/In-person | Team Aces | Zoom, Email, Classroom
|  | Feedback regarding project documentation | Bi-weekly till 27th April 2022 | Online/In-person | Team Aces | Zoom, Email, Classroom
4 | Public/Citizen | Interaction during survey | Daily During Public Survey phase | Online | Team Aces | Zoom, Email
|  | Awareness about Light Pollution and Eco-friendly light usage | Post-funding phase | Online/In-person | Team Aces | Zoom, Webex, Email, Campaign
5 | Angel Investors | Presenting the Project Idea | On 27th April,2022 | In-person/Online | Team Aces | Zoom, Classroom
|  | Discussing Capital Investment | On 27th April,2022 | In-person/Online | Team Aces | Zoom, Classroom
6 | Competitiors | Survey feedback regarding Light Pollution and impacts | Once During Survey phase | Online | Team Aces | Zoom, Webex, Email
|  | Discussing future collaboration | Once during Design Plan | Online/In-person | Team Aces | Zoom, Webex, Office, Email
7 | PETA (Animal Right Association) | Information on impacts of Light Pollution on Animals and Fishes | Once During Survey phase | Online | Team Aces | Zoom, Webex, Email
8 | NYC DOT (Department of Transportation) | Survey feedback regarding street light installation | Once During Survey phase | Online | Team Aces | Zoom, Webex, Email
|  | Information about future outdoor e-lighting plans | Once During Market Research phase | Online | Team Aces | Zoom, Webex, Email
9 | Illuminating engineering society (IES) | Survey feedback regarding Good lighting practises | Once During Survey phase | Online | Team Aces | Zoom, Webex, Email
10 | NYC DEP(Department of Environmental Protection) | Survey feedback on Light Pollution and impacts on Environment | Once During Survey phase | Online | Team Aces | Zoom, Webex, Email
11 | NYC DEC(Department of Environmental Conservation) | Survey feedback on Light Pollution and impacts on Environment | Once During Survey phase | Online | Team Aces | Zoom,Webex,Email
12 | Volunteers | Status of the Project | Weekly from Kick-off to Closing of Project | Online/In-person | Team Aces | Zoom, Classroom, Residence
|  | Task Allocation | Bi-weekly from kick-off to closing of project | Online/In-person | Team Aces | Zoom, Classroom, Residence
|  | Campaign, seminars and community engagement events planning | Post-funding phase | Online/In-person | Team Aces | Zoom, Webex, Office, Email
13 | New York Health Department | Information regarding impacts of Light Pollution on Human Health | Once During Survey phase | Online | Team Aces | Zoom, Webex, Email